## Info
Project Workbook Information
The project workbook allows project managers, team members, sponsors, and stakeholders to easily track and monitor project activities. Any of these worksheets can easily be broken out into separate documents.
Suggested Sheets for All Projects
Data | Filling out the Data sheet completes the header portion of all remaining sheets in the project workbook.
Minicharter | The Project Minicharter sheet can be used as a charter for small projects or a summarization of a full charter for larger projects.
Stoplight | The Stoplight Report sheet contains a status report that can be used to keep sponsors, team members, and stakeholders informed of project progress.
Budget | The Budget sheet allows you to track original budget, expenditures to date, and any cost variance.
CBA | The Cost/Benefit Analysis sheet allows you to review the proposed project and potential alternatives and make a project selection based on a greater ROI (return on investment).
Risks | The Risk Management Matrix sheet allows you to identify, qualify, quantify, and prioritize risks (events that might happen; the uncertainty of a project), create mitigation and contingency plans, and assign risks owners.
Issues | The Issues Log sheet allows you to identify and monitor project issues (unplanned events that have happened).
Action | The Action Items sheet allows you to track and monitor action items assigned to team members. Action items are tasks that must be done but are too insignificant from a time perspective to track in your project schedule.
Miles | The Deliverable Milestones sheet allows you to identify major deliverable milestones and the due dates, objectives, assumptions, and constraints relevant to that deliverable milestone.
WBS | The Work Breakdown Structure sheet includes the activities that must be completed during a project, the effort required, all relevant dates, and the resources assigned to do the work.
Roster | The Roster sheet provides contact information for all those involved on the project.
R&R | The Roles and Responsibilities sheet shows the primary role of team members, any deliverables in which they are involved, and the percentage of time they are expected to work on the project.
RAM | The Resource Assignment Matrix sheet shows you what type of resource is responsible for, or somehow involved with, each deliverable. The tasks listed are samples; you should update the RAM with tasks appropriate for your project.
RCM | The Resource Commitment Matrix sheet shows how many effort hours each person on the project has been allocated by month.
A&C | The Assumptions and Constraints sheet allows you to track project assumptions and constraints.
Decision | The Decision Log sheet allows you to track all major decisions made during the course of the project.
Comm | The Communication Plan sheet allows you to detail your communication plan: how you are going to communicate, whom you will be communicating with, how often, in what format, etc.
Stake | The Stakeholder Analysis sheet allows you to identify stakeholders, their role, and their requirements.
Expectations | The Expectations sheet allows you to identify and track the expectations of various stakeholders.
Chg Log | The Change Control Log sheet allows you to track all change requests that are in process or finalized.
Deliver | The Deliverable Acceptance Log sheet allows you to track the status of deliverable acceptances.
PERT | The PERT Analysis sheet allows you to perform PERT analysis on WBS tasks.
Delphi | The Delphi Exercise sheet allows you to develop estimates for WBS tasks through the Delphi technique.
TimeSum | The Timesheet Totals sheet allows you to track effort hours of your entire team by individual and by month.
Timesheet | The Timesheet can be used by each team member to submit effort hours by activity, by month.
Size Est | The Initial Project Size Estimate sheet allows you to estimate, at high-levels (40,000 ft. view), the size of a project. This estimate should not be considered final as requirements and technical specifications typically have not been fully developed yet.
Res Load | The Resource Loading sheet allows you to identify the work effort required, the duration, and the allowed commitment level of each person assigned to the project.
Qual Metrics | The Project Quality Metrics sheet allows you to identify critical success criteria, related quality metrics, and their priority.
Project Register | The Project Register sheet allows you to identfy executive champions, goal/strategy alignment, and order of magnitude.
Portfolio Review | The Portfolio Review sheet identifies the CPI and SPI, status, and recommendations for each project in the portfolio.
© Global Knowledge Network, Inc.

## Data
Project | Project title here
Project # | Project # here
Project manager | Project manager name here
Sponsor | Sponsor name here
Project artifacts | Location of project documents here
Last updated | Date of update here
© Global Knowledge Network, Inc.

## Minicharter
Project Minicharter
Project | Project title here | Project # | Project # here
Project manager | Project manager name here | Sponsor | Sponsor name here
Project artifacts | Location of project documents here | Updated | Date of update here
Background
Business need and business benefits
Objectives
Scope | In Scope | Out of Scope
Deliverables | Deliverable | Due Date
Flexibility matrix | Scope
Schedule
Cost
Key considerations | Assumptions & Constraints | Risks
|  | Category | Risk Description
Success criteria | 1 -
2 -
3 -
4 -
5 -
Signatures
Sponsor
Signature
Printed name
Date
Project manager
Signature
Printed name
Date
© Global Knowledge Network, Inc.
Note on B19: Note A for assumptions, C for constraints
Note on C16: Options are: Most flexible Moderately flexible Least flexible
Note on C17: Options are: Most flexible Moderately flexible Least flexible
Note on C18: Options are: Most flexible Moderately flexible Least flexible
Note on C20: This is a field you can use to identify risks by categories such as technological, personnel, etc.

## Stoplight
Stoplight Report
Project | Project title here |  |  |  |  | Project # | Project # here
Project manager | Project manager name here |  |  |  |  | Sponsor | Sponsor name here
Project artifacts | Location of project documents here |  |  |  |  | Updated | Date of update here
Deliverables
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Schedule
Scope
Cost
Risk
Issues
Planned completion
Est. completion
Management Alert
ID | Situation Requiring Management Attention |  |  |  | Action Plan |  |  |  | Owner
Accomplishments During Reporting Period
ID | Description of Accomplishment |  |  | Planned Completion | Date Completed | Owner |  | Comments
Deliverables | Title/Description |  |  |  |  | Title/Description
1 |  |  |  |  | 6
2 |  |  |  |  | 7
3 |  |  |  |  | 8
4 |  |  |  |  | 9
5 |  |  |  |  | 10
© Global Knowledge Network, Inc.
Note on A28: In Row 7 there are 10 deliverables listed. This section allows you to explain each deliverable.
Note on B8: Options are: Green: On schedule/on budget Yellow: Somewhat behind schedule/somewhat over budget Red: Behind schedule/over budget

## Budget
Budget
Project | Project title here | Project # | Project # here
Project manager | Project manager name here | Sponsor | Sponsor name here
Project artifacts | Location of project documents here | Updated | Date of update here
Budget Status
Approved Budget | Planned Expenditures to Date | Actual Expenditures to Date | Variance
0 | 0 | 0 | 0
| Planned Remaining Budget | Actual Remaining Budget | Variance
| 0 | 0 | 0
Additional $ needed
Budget Details
Internal Expenses
Salaries | Hourly Rate | # Hours | Total Cost
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Other Internal Expenses |  |  | Total Cost
Type of expense |  |  | 0
Type of expense |  |  | 0
Type of expense |  |  | 0
Total Internal Expenses |  |  |  | 0
External Expenses
Consulting Costs |  |  | Total Cost
Type of consulting |  |  | 0
Type of consulting |  |  | 0
Type of consulting |  |  | 0
Capital Expenditures |  |  | Total Cost
Type of expense |  |  | 0
Type of expense |  |  | 0
Type of expense |  |  | 0
Total External Expenses |  |  |  | 0
Total Budget |  |  |  | 0
© Global Knowledge Network, Inc.

## CBA
Cost/Benefit Analysis
Project | Project title here |  |  | Project # | Project # here
Project manager | Project manager name here |  |  | Sponsor | Sponsor name here
Project artifacts | Location of project documents here |  |  | Updated | Date of update here
Project Development and Maintenance Costs
Description | FY01 | FY02 | FY03 | FY04 | FY05 | Total
Cost of Project Development
Salaries
Other internal expenses
Consulting costs
Capital expenditures
Total project costs | 0 | 0 | 0 | 0 | 0 | 0
Cost of Support
Operational costs
Nonrecurring costs
Recurring costs
Total ongoing support costs | 0 | 0 | 0 | 0 | 0 | 0
Benefits/Savings
Current Process | FY01 | FY02 | FY03 | FY04 | FY05 | Total
Total annual price
New Process
Total annual price
Annual savings | 0 | 0 | 0 | 0 | 0 | 0
Cumulative savings | 0 | 0 | 0 | 0 | 0 | 0
Cumulative costs | 0 | 0 | 0 | 0 | 0 | 0
Cumulative total net savings | 0 | 0 | 0 | 0 | 0 | 0
Future Value
Present Value | Interest Rate |  | # Periods |  | Future Value
0
Present Value
Future Value | Interest Rate |  | # Periods |  | Present Value
0 |  |  |  |  | 0
Net Present Value
Period | Cash Flow |  |  |  | Present Value
1
2
3
4
5
Totals | 0 |  |  |  | 0
Project development cost |  |  |  |  | 0
Net present value |  |  |  |  | 0
© Global Knowledge Network, Inc.
Note on A32: How much is the money worth today?
Note on A36: This is how much money you expect the project to be worth.
Note on B40: FV for the period's return. Note: Change the PV # Periods to match the Period here.
Note on D32: How many years will the project last?
Note on D36: How many years will it take until the company starts seeing this profit?
Note on F32: This is how much money you expect the project to be worth.
Note on F36: This is how much the money you project making would be worth in today's market.
Note on F40: This is how much the money you project making would be worth in today's market.

## Risks
Risk Management Matrix (Risk Register)
Project |  |  | Project title here | [5 empty] | Project # | Project # here
Project manager |  |  | Project manager name here | [5 empty] | Sponsor | Sponsor name here
Project artifacts |  |  | Location of project documents here | [5 empty] | Updated | Date of update here
ID | Risk Description | Probability | Impact | Detectability | Importance | Category | Trigger Event/Indicator | Risk Response and Description | Contingency Plan | Owner | Status | Date Entered | Date to Review
1 | What is this risk? |  |  |  | 0 |  | What act or event initiates either the risk occurrence or precipitates the response strategy? | How will you respond to this risk and what actions will you take to match that response? | If the risk becomes a reality, what will you do in response, as a backup, or alternative/ workaround? | Who monitors this risk?
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
© Global Knowledge Network, Inc.
Note on C6: Probability: 4: Highly likely/probable (76%-100%) 3: Likely (51%-75%) 2: Somewhat likely (26%-50%) 1: Unlikely/improbable (0%-25%)
Note on D6: Impact: 4: Critical: Threatens the viability of the business or represents failure of the project 3: Severe: Threatens the achievement of business vision or severely reduces project benefits 2: Moderate: May delay achievement of the vision or reduce project benefits 1: Minimal/minor: No impact on business vision but may increase project costs and timescales
Note on E6: Detectability: 4: Determined after impact has been realized 3: Realized upon trigger event 2: Immediately prior to trigger event; can be mitigated prior to trigger if monitored 1: Determined well in advance of occurrence or trigger event
Note on G6: This is a field you can use to identify risks by categories such as technological, personnel, etc.
Note on I6: Options are: Avoidance Transference Mitigation Acceptance Include a description of what actions are taken to implement the response.
Note on L6: Options are: Open Closed

## Issues
Issues Log
Project |  | Project title here |  | Project # | Project # here
Project manager |  | Project manager name here |  | Sponsor | Sponsor name here
Project artifacts |  | Location of project documents here |  | Updated | Date of update here
ID | Issue Description | Project Impact | Action Plan/Resolution | Owner | Importance | Date Entered | Date to Review | Date Resolved
1 | What is the issue? | How will this impact scope, schedule & cost? | How do you intend to deal with this issue? | Who manages this issue?
2
3
4
5
6
7
8
9
10
11
12
13
14
15
© Global Knowledge Network, Inc.
Note on F6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low

## Action
Action Items
Project |  | Project title here |  |  | Project # | Project # here
Project manager |  | Project manager name here |  |  | Sponsor | Sponsor name here
Project artifacts |  | Location of project documents here |  |  | Updated | Date of update here
ID | Action Item | Owner | Status | Date Entered | Planned Completion | Actual Completion | Comments
1 | What is the item to be completed? | Who manages this issue?
2
3
4
5
6
7
8
9
10
11
12
13
14
15
© Global Knowledge Network, Inc.
Note on D6: Options are: Open Closed

## Miles
Deliverable Milestones
Project |  | Project title here |  |  | Project # | Project # here
Project manager |  | Project manager name here |  |  | Sponsor | Sponsor name here
Project artifacts |  | Location of project documents here |  |  | Updated | Date of update here
ID | Milestone | Description | Planned Completion | Actual Completion | Objectives | Assumptions | Constraints
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
© Global Knowledge Network, Inc.

## WBS
Work Breakdown Structure
Project |  | Project title here |  |  |  | Project # | Project # here
Project manager |  | Project manager name here |  |  |  | Sponsor | Sponsor name here
Project artifacts |  | Location of project documents here |  |  |  | Updated | Date of update here
ID | Task | Dependencies | Status | Effort Hours | Cost | Start Date | Planned Completion | Estimate to Completion | Actual Completion | Resource
1 |  | ID # of task
2
3
4
5
6
7
8
9
10
11
12
13
14
15
© Global Knowledge Network, Inc.
Note on D6: Options are: Open Closed

## Roster
Roster
Project | Project title here |  |  |  | Project # | Project # here
Project manager | Project manager name here |  |  |  | Sponsor | Sponsor name here
Project artifacts | Location of project documents here |  |  |  | Updated | Date of update here
Name | Core/ Extended Team | Title | Dept. | Phone | Cell Phone | E-Mail | Project Role
|  |  |  | 000.000.0000 | 000.000.0000
© Global Knowledge Network, Inc.

## R&R
Roles and Responsibilities
Project | Project title here |  |  |  | Project # | Project # here
Project manager | Project manager name here |  |  |  | Sponsor | Sponsor name here
Project artifacts | Location of project documents here |  |  |  | Updated | Date of update here
Name | Core/ Extended Team | % Assigned | Deliverables Leading | Deliverables Participating On | Project Role | Responsibility | Other Project Assignments
© Global Knowledge Network, Inc.

## RAM
Resource Assignment Matrix
Project |  |  | Project title here |  | Project # | Project # here
Project manager |  |  | Project manager name here |  | Sponsor | Sponsor name here
Project artifacts |  |  | Location of project documents here |  | Updated | Date of update here
Project Task
Project Management and Requirements
Initiation
1
2
3
4
5
Planning
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
Execution
1
2
3
4
5
6
Closing
1
2
3
4
5
6
7
Legend
| Creates the deliverable |  |  | C1: primary creator; C2: contributor
| Input required |  |  | I
| Reviews the deliverable |  |  | R
| Approves the deliverable |  |  | A
| Notified when the deliverable is complete |  |  | N
| Owns the deliverable upon completion |  |  | O
© Global Knowledge Network, Inc.
Note on D10: Insert project tasks for this phase in this column.
Note on D17: Insert project tasks for this phase in this column.
Note on D42: Insert project tasks for this phase in this column.
Note on D50: Insert project tasks for this phase in this column.
Note on E6: Insert team member roles in this row.

## RCM
Resource Commitment Matrix
Project | Project title here |  |  |  |  | Project # |  | Project # here
Project manager | Project manager name here |  |  |  |  | Sponsor |  | Sponsor name here
Project artifacts | Location of project documents here |  |  |  |  | Updated |  | Date of update here
Effort Hours Committed
Names | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
© Global Knowledge Network, Inc.

## A&C
Assumptions and Constraints
Project |  | Project title here | Project # | Project # here
Project manager |  | Project manager name here | Sponsor | Sponsor name here
Project artifacts |  | Location of project documents here | Updated | Date of update here
ID | Description | Comments | Type | Status | Date Entered
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
© Global Knowledge Network, Inc.
Note on D6: Options are: A: assumption C: constraint
Note on E6: Options are: Open Closed

## Decision
Decision Log
Project |  | Project title here | Project # | Project # here
Project manager |  | Project manager name here | Sponsor | Sponsor name here
Project artifacts |  | Location of project documents here | Updated | Date of update here
ID | Decision Description | Comments | Owner | Status | Date Entered
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
© Global Knowledge Network, Inc.
Note on D6: Who made the decision?
Note on E6: Options are: Open Closed

## Comm
Communication Plan
Project |  | Project title here | Project # | Project # here
Project manager |  | Project manager name here | Sponsor | Sponsor name here
Project artifacts |  | Location of project documents here | Updated | Date of update here
ID | Communication | Description | Frequency | Format | Owner | Recipient/ Attendees
1 | What type of communication is this? | What is the description of the contents/purpose of this communication? |  |  | Who sends? | Who gets?
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
© Global Knowledge Network, Inc.
Note on B7: Examples: Executive status report Team status report
Note on E6: Examples: E-mail Meeting

## Stake
Stakeholder Analysis
Project |  | Project title here | Project # | Project # here
Project Manager |  | Project manager name here | Sponsor | Sponsor name here
Project Artifacts |  | Location of project documents here | Updated | Date of update here
ID | Stakeholder | Role | Impact | Influence | Risk Tolerance | Needs | Responsibility
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
© Global Knowledge Network, Inc.
Note on D6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low
Note on E6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low

## Expectations
Expectations
Project | Project title here | Project # |  | Project # here
Project manager | Project manager name here | Sponsor |  | Sponsor name here
Project artifacts | Location of project documents here | Updated |  | Date of update here
ID | Expectation Description | Source | Must Have | Want to Have | Nice to Have | Date Identified
© Global Knowledge Network, Inc.

## Chg Log
Change Control Log
Project |  | Project title here |  |  |  | Project # | Project # here
Project Manager |  | Project manager name here |  |  |  | Sponsor | Sponsor name here
Project Artifacts |  | Location of project documents here |  |  |  | Updated | Date of update here
ID | Change Description | Priority | Originator | Date Entered | Date Assigned | Evaluator | Status | Date of Decision | Included in Rev. #
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
© Global Knowledge Network, Inc.
Note on C6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low
Note on D6: Who identified the change needed?
Note on G6: Who will decide what action is taken on the change?
Note on H6: Options are: In review Rejected Deferred Approved
Note on J6: Options are: No Rev. #

## Deliver
Deliverable Acceptance Log
Project |  | Project title here | Project # | Project # here
Project manager |  | Project manager name here | Sponsor | Sponsor name here
Project artifacts |  | Location of project documents here | Updated | Date of update here
ID | Deliverable Description | Comments | Evaluator | Status | Date of Decision
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
© Global Knowledge Network, Inc.
Note on E6: Options are: In review Rejected Accepted

## PERT
PERT Analysis
Project |  | Project title here | [5 empty] | Project # |  | Project # here
Project Manager |  | Project manager name here | [5 empty] | Sponsor |  | Sponsor name here
Project Artifacts |  | Location of project documents here | [5 empty] | Updated |  | Date of update here
ID | Task | Most Likely | Min | Max | PERT Est | 15/15 Comp'ed Est | Std Dev | +1 Std Dev | -1 Std Dev | +2 Std Dev | -2 Std Dev | +3 Std Dev | -3 Std Dev
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
© Global Knowledge Network, Inc.

## Delphi
Delphi Exercise
Project | Project title here |  |  |  |  | Project # |  | Project # here
Project manager | Project manager name here |  |  |  |  | Sponsor |  | Sponsor name here
Project artifacts | Location of project documents here |  |  |  |  | Updated |  | Date of update here
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
© Global Knowledge Network, Inc.

## TimeSum
Timesheet Totals
Project | Project title here |  |  |  |  | Project # |  | Project # here
Project manager | Project manager name here |  |  |  |  | Sponsor |  | Sponsor name here
Project artifacts | Location of project documents here |  |  |  |  | Updated |  | Date of update here
Effort Hours Spent
Name | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
© Global Knowledge Network, Inc.

## Timesheet
Timesheet
Project | Project title here |  |  |  |  | Project # |  | Project # here
Project manager | Project manager name here |  |  |  |  | Sponsor |  | Sponsor name here
Project artifacts | Location of project documents here |  |  |  |  | Updated |  | Date of update here
Name | Insert name here
Effort Hours Spent
Task | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
© Global Knowledge Network, Inc.

## Size Est
Initial Project Size Estimate
Project |  | Project title here | Project # | Project # here
Project manager |  | Project manager name here | Sponsor | Sponsor name here
Project artifacts |  | Location of project documents here | Updated | Date of update here
Scope Estimate
Technology Systems Impacted
|  | 1 to 2 | 3 to 5 | 6 or more
# of Business Requirements | Less than 50 | Automatically do; no approval needed
51 - 100
| 100 or more |  |  | Approval required
Cost Estimate
# of Resources Involved
|  | Less than 10 | 11 to 50 | 51 or More
# of Business Requirements | Less than 50 | Automatically do; no approval needed
51 - 100
| 100 or more |  |  | Approval required
Cost Estimate
# of Resources Involved
|  | Less than 10 | 11 to 50 | 51 or More
Benefit | Low |  |  | Avoid
Medium
| High | Automatically do; no approval needed
© Global Knowledge Network, Inc.

## Res Load
Resource Loading
Project | Project title here |  | Project # | Project # here
Project manager | Project manager name here |  | Sponsor | Sponsor name here
Project artifacts | Location of project documents here |  | Updated | Date of update here
Team Member:
Effort Hours Committed
ID | Task | Effort Hours | Duration (Weeks) | Available Hours | Commitment Level
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
| Total | 0 | 0 | 0 | #DIV/0!
© Global Knowledge Network, Inc.
Note on C7: Estimate of total hours needed for this task
Note on E7: Number of hours that member has available
Note on F7: Available Hours divided by Duration (Weeks). However, if Effort Hours is less than Available Hours, then Effort Hours divided by Duration (Weeks).

## Qual Metrics
Project Quality Metrics
Project | Project title here |  | Project # | Project # here
Project Manager | Project manager name here |  | Sponsor | Sponsor name here
Project Artifacts | Location of project documents here |  | Updated | Date of update here
ID | Critical Success Criteria | Potential Quality Metric |  | Priority | Metric Target | Action Plan
© Global Knowledge Network, Inc.

## Project Register
Project Register
Project |  | Project title here |  | Project # | Project # here
Project manager |  | Project manager name here |  | Sponsor | Sponsor name here
Project artifacts |  | Location of project documents here |  | Updated | Date of update here
Order of Magnitude
ID | Project Name | Description | Category | Executive Champion | Goal/Strategy Alignment | Time | Costs | Return | Status | Rank
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Note on C7: Brief description of proposed project
Note on D7: Type of project (e.g., product development, market expansion, legal requirement, regulatory mandate, strategic)
Note on E7: Executive team member serving as primary champion or "cheerleader" for the project
Note on F7: Organizational goals and/or strategic objectives that align with project
Note on G7: Options are: 4: > 2 years 3: > 1 year 2: 6 - 12 months 1: 0 - 6 months
Note on H7: Options are: 4: > $1 million 3: > $500,000 2: $100,000 - $500,000 1: Up to $100,000
Note on I7: Options are: 4: 1 - 6 months 3: 6 - 24 months 2: 2 years+ 1: never
Note on J7: Options are: Active Approved Rejected Under review Postponed
Note on K7: Priority of this project compared to the other projects in the portfolio

## Portfolio Review
Periodic Portfolio Review Report
Project |  | Project title here |  | Project # | Project # here
Project manager |  | Project manager name here |  | Sponsor | Sponsor name here
Project artifacts |  | Location of project documents here |  | Updated | Date of update here
|  |  |  | Analysis |  | Status
ID | Project Name | Description | Rank | Costs (CPI) | Schedule (SPI) | Time | Costs | Scope | Return | Recommendation
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Note on G6: Options: Red: Significantly off target Yellow: Off target or trending outside of acceptable limits Green: On target Blue: Requires executive attention or awaiting critical decision(s)
Note on K7: Options: Proceed Cancel Suspend Re-Prioritize